## Sheet1
file names for each features
|  |  |  | Feature no. | Features | Controller | Model | View
Task Name | Start | End | Duration (days) |  | Post page
|  |  |  | 1 | As an school admin, I can post news and updates | PostController.php | postmodel.php | * index.php * post.php | Steps in creating the file
CITE Circle | 2016-04-23 | 2016-08-30 | 129 | 2 | As a user, I can see news and updates posted by the school admin | PostController.php | postmodel.php | * index.php * post.php | 1. create a folder name after the page (in Controller, Model, and View folder)
Iteration 1 | 2016-04-27 | 2016-05-12 | 15 | 3 | As a user, I can up vote news and Updates posted by the School admin | PostController.php | postmodel.php | * index.php * post.php | 2. create the file naming them base on the table
Post Page |  |  |  | 4 | As a user, I can post | PostController.php | postmodel.php | * index.php * post.php
Coding | 2016-04-27 | 2016-05-05 | 8 | 5 | As a user, I can edit my post | PostController.php | postmodel.php | * index.php * post.php
Testing | 2016-05-02 | 2016-05-11 | 9 | 6 | As a user, I can comment posts | PostController.php | postmodel.php | * index.php * post.php
Profile Page |  |  |  | 7 | As a user, I can delete my Post | PostController.php | postmodel.php | * index.php * post.php
Coding | 2016-04-27 | 2016-05-05 | 8 |  | Profile Page
Testing | 2016-05-02 | 2016-05-11 | 9 | 8 | As a user, I can Edit my Profile | ProfileController.php | profilemodel.php | *edit.php
Release | 2016-05-12 | 2016-05-12 | 0 | 9 | As a User, I can Upload a picture for my profile | ProfileController.php | profilemodel.php
Iteration 2 | 2016-05-12 | 2016-05-28 | 16 | 10 | As a User, I can view my profile | ProfileController.php | profilemodel.php | *index.php
Planning | 2016-05-14 | 2016-05-14 | 0
0
Meetings |  | For Task Management goto:
* Saturday meeting |  | http://localhost/task/
Checking status
* Monday Meeting
Remind Task |  | For Repository:
https://github.com/jeremiahC/cite_circle
2 weeks coding
For Demo
End Target